## Questions
Use this form during the PSSR meeting. Circle response to each question; if answer is 'yes' action item shall be generated. Record actions on next sheet and obtain signatures of attendees.
RESPONSE |  |  |  | ITEM | PRIORITY
Yes | No | N/A | NC | Is there special training that must be completed before employee uses equipment? (operations, lab, maintenance, shipping, ERT) | A OR B
Yes | No | N/A | NC | Do SOP's or work instructions need to be written, updated or added to Compliant Pro? Including normal and emergency operations | A
Yes | No | N/A | NC | Is a flow sheet required? Will flow sheet need to be made available in the control room? | B
Yes | No | N/A | NC | Do As-built drawings need to be updated? (P&ID’s, electrical, loop sheets, piping, mechanical, underground) | C
Yes | No | N/A | NC | Do red lined drawings need to be provided in the control room? | A
Yes | No | N/A | NC | Does the LOTO need to be updated? | B
Yes | No | N/A | NC | Does any process technology require updates? (for example, interlock lists, P&ID’s, logic drawings, PSI etc.)? | C
Yes | No | N/A | NC | Does Safety Shower, PSV, Fire Extinguisher, SCBA checklist need to be updated? | B
Yes | No | N/A | NC | Is any special PPE required? Does it need to be made available? | A
Yes | No | N/A | NC | If a PHA/HAZOP was required are there still open actions required before startup? | A
Yes | No | N/A | NC | Are the operating conditions outside of the design conditions? MAWP/MAWT | A
Yes | No | N/A | NC | Do changes made during construction need to be recorded or authorized? When deviating from the original scope of the MOC changes must be reviewed and approved. | A
Yes | No | N/A | NC | Does the reactivity matrix need to be updated? - consider the hazardous effects of inadvertent mixing of different materials | A
Yes | No | N/A | NC | Does the Hazardous Material PPE guide need to be updated? | B
Yes | No | N/A | NC | Have SDS Sheets and Quicklists been made available? | A
Yes | No | N/A | NC | Have HMIS/NFPA Numbers been made available? | A
Yes | No | N/A | NC | Industrial Hygiene monitoring needed? | C
Yes | No | N/A | NC | If monitoring tubes or badges required do they need to be made available? | C
Yes | No | N/A | NC | Have appropriate changes to the air permit been completed? | A
Yes | No | N/A | NC | If Area Spill Procedures are required, do they need to be made available? Does SPCC plan need updating? | B
Yes | No | N/A | NC | Do materials used in the system need to be entered on the Area Chemicals Inventory List (or equivalent)? RQ list need updating? | B
Yes | No | N/A | NC | Does new or revised piping, valves and equipment need drawing updates for fugitive monitoring? (HON/MON/MACT) (Contact Environmental) | C
Yes | No | N/A | NC | Are there any special handling requirements for wastes? Do adequate arrangements need to be made, prior to start-up, for the identification, classification and safe disposal of all waste materials? DRW#? | A
Yes | No | N/A | NC | Does equipment need to be grounded? | A
Yes | No | N/A | NC | Does lighting need to be upgraded? | B
Yes | No | N/A | NC | Are electrical boxes exposed? | A
Yes | No | N/A | NC | Are changes necessary to on/off controls to match plant design? Start/green/top Stop/red/bottom Review Hand/Off/Auto & Jog/Off/Auto for appropriate set up | B
Yes | No | N/A | NC | Does electrical equipment need to be labeled? Label all electric switches, start/stop switches, disconnects, MCCs, Control panels, cables and wires from the instrument to junction box to terminal block and back to the house. | A
Yes | No | N/A | NC | Do new switch-gear or circuit breakers need to be labeled? | A
Yes | No | N/A | NC | Does electrical equipment need to be tested? | A OR B
Yes | No | N/A | NC | Are changes needed to meet electrical classification of the area? Are changes needed to the electrical classification map? | A OR B
Yes | No | N/A | NC | Do any new Sub-station Breakers, MCC isolators, starters or other appropriate equipment need to be added to SAP and PM's created as needed? | C
Yes | No | N/A | NC | Any other obvious electrical problems? | A OR B
Yes | No | N/A | NC | Will equipment need additional instruments and alarms in order to maintain safe operation? | A OR B
Yes | No | N/A | NC | Do instruments need to be recalibrated where necessary? (Note: Make sure all Level, flow and pressure transmitters have been recalibrated for any changes in specific gravities and needed flow or pressure controls) | A
Yes | No | N/A | NC | Have consequences of instrument or computer failure (redundancy, backup power supply, or others) been considered? XCVs should fail to the safe position | A
Yes | No | N/A | NC | Are there instruments on the system that still require a calibration and function test? (Keep a checklist of when the loop tested, by whom, and the test results.) | A OR B
Yes | No | N/A | NC | Does the control logic need to be added to the P&ID? Ensure the logic is on the P&ID for Maint/operation reference. | C
Yes | No | N/A | NC | Does the software need to be properly documented and filed? (for example, logic drawings, schematics, sequence/batch descriptions, FR)? | C
Yes | No | N/A | NC | Do the process graphics need to be updated? Graphics must be updated, checked and tested prior to running the system. | A
Yes | No | N/A | NC | Does the logic need to be tested to ensure its purpose? Consider where equipment restarts automatically such as when an interlock clears or re-establishment of power after an outage | A OR B
Yes | No | N/A | NC | Are additional safety showers and eye baths required? Are changes required to ensure path is unobstructed? | A
Yes | No | N/A | NC | Has existing safety equipment (extinguishers, safety showers, monitors etc.) been compromised due to the new or revised piping and equipment installed. | A
Yes | No | N/A | NC | Is there a need for additional fire protection equipment or changes to existing equipment? | A
Yes | No | N/A | NC | Do cages and swing gates need to be installed on ladders? | A
Yes | No | N/A | NC | Does emergency access and egress need to be provided? | A
Yes | No | N/A | NC | Are changes needed to provide adequate work area and ventilation around equipment? | A
Yes | No | N/A | NC | Do any Valves handles interfere with normal operation? | A
Yes | No | N/A | NC | Do block valves before or after safety valves need to be Car Sealed Open or Locked Open? Add to monthly checklist if new. | A
Yes | No | N/A | NC | Does equipment location cause interference with safe operation or maintenance work? | A
Yes | No | N/A | NC | Does grating need to be bolted down? Is there a need for hand rails? | A
Yes | No | N/A | NC | Have tripping hazards or head knockers been created? | A
Yes | No | N/A | NC | Does the job site need to be properly cleaned-up? | A OR B
Yes | No | N/A | NC | Are changes needed to ensure hoses installed properly (acceptable material of construction, bleed off points, current inspection, etc.) | A
Yes | No | N/A | NC | Do provisions need to be made for safe routine sampling? | A
Yes | No | N/A | NC | Do vents and drains create a hazard when in use? | A
Yes | No | N/A | NC | Are all secondary containment/bonding facilities adequate (bulk liquid chemicals, etc.)? | C
Yes | No | N/A | NC | Have all underground pipe routes/connections been physically verified (uncovered, flow test, etc.) provide documentation | A
Yes | No | N/A | NC | Any issues with thermal expansion and/or proper clearing (i.e. bleeders, check valves, isolation valves, equalization line, expansion joints)? | A
Yes | No | N/A | NC | Will steam traps need to be repositioned in order to discharge in a safe location? | A
Yes | No | N/A | NC | Do cross-ties need to be blinded where there is a chance of contamination? | A
Yes | No | N/A | NC | Does protection need to be provided against overpressure or excess vacuum? | A
Yes | No | N/A | NC | Do relief valve vents require modification in order to vent to a safe location? | A
Yes | No | N/A | NC | Do coupling guards need to be installed on rotating equipment? | A
Yes | No | N/A | NC | Does the seal fluid need to be changed or charged to the system? | A
Yes | No | N/A | NC | Do caps or plugs need to be installed on bleeders and hose connections? | A
Yes | No | N/A | NC | Does safety/personnel insulation protection need to be installed? Are there other potential thermal exposure issues? (temp wrap or barricading required before startup where there is a risk of personnel burn, otherwise to be completed after startup) | A
Yes | No | N/A | NC | Does tracing need to be installed, turned on or labeled for easy identification? | A OR B
Yes | No | N/A | NC | Has equipment been installed to specifications? (Proper gasket material, proper piping material) | A
Yes | No | N/A | NC | For ball valves installed in oxide service does the ball still need to be drilled? Does the P&ID need to be updated with the direction of the drilled ball? | A
Yes | No | N/A | NC | Are modifications needed for drainage to be adequate for operation? | A OR B
Yes | No | N/A | NC | Does system/equipment need additional backflow protection? | A
Yes | No | N/A | NC | Does the equipment or piping need additional supports? | A OR B
Yes | No | N/A | NC | Do piping flanges have any Hi/Lo misalignment or gapping issues? | A
Yes | No | N/A | NC | Does piping and equipment need to be labeled? | A
Yes | No | N/A | NC | Does the equipment (piping, vessels) need to be tested for leaks? i.e. pressure/vacuum test, hydro, snoop test, etc. NOTE: For returning flammables to service see PROC-01754 NOTE2: For High Pressure Hydrogen reactor systems only. Piping and equipment must be pressure tested with nitrogen to at least 400 psig and flanges, valves and fittings soaped checked. | A
Yes | No | N/A | NC | Do equipment files need to be stored in the Engineering file room or electronically? | C
Yes | No | N/A | NC | Are spare parts for equipment/ critical equipment needed? | C
Yes | No | N/A | NC | New maintenance procedures required? | B
Yes | No | N/A | NC | Does a Preventative Maintenance (PM) need to be created or modified? | C
Yes | No | N/A | NC | Does a reliability engineering analysis need to be completed for PSM critical equipment? PSCE list | B
Yes | No | N/A | NC | Does a Mechanical integrity program need to be implemented for new unit or process change? | C
Yes | No | N/A | NC | Are code plates required for new pressure vessels? | A

## PSSR AI List
PSSR Action Item List
No. | Action Item Description | Responsible Person | Required Before Startup, Yes/No
1
2
3
4
5
6
7
8
PSSR Sign in Sheet
When checked, the corresponding signatures are required.
| Area Employee Rep.; _____________________________ |  | Date: ______________
| Area Management Rep.; _____________________________ |  | Date: ______________
| HSE Rep.: _____________________________ |  | Date: ______________
| Area Maintenance Rep.: _____________________________ |  | Date: ______________
| Engineering Rep: _____________________________ |  | Date: ______________
| Other ( ): _____________________________ |  | Date: ______________
Comments:
_____________________________________________________________________________________
_____________________________________________________________________________________
_____________________________________________________________________________________
*NOTE: This form is for field walk through ONLY. All action items must be entered into pmOps
with assignment of the responsible person and completion dates.